## DARE Application
Acronym Ventures Ltd
DARE Application - Progress Tracker Template
| Document | Description | Owner | Reviewer | XReg Lead | Acronym Lead | CTM Lead | Deadline | Status | Status 2 | Comments
| Application for Registration | To be updated with new requirements for DARE Act 2024 | [5 empty] | Submission of application in principle: XXX 2025 Request full approval: XXX 2025
1 | Part A - Form 1 (Registration as Digital Asset Business) (Required for SCB Approval in-principle) | Main application form to include all company details | XReg: | Acronym: |  |  |  | XR handoff to CTMCo: | Completed |  | New application forms drafted. Filled in where possible - Need the following info: - Telephone Number for [Owner] - Signed and dated by [Owner] and [Owner]--- file uploaded
2 | Part A - Form 2 (Director/UBO/Officer/SIH) (Required for SCB Approval in-principle) | A personal questionnaire for all directors/UBOs/senior officers/significant interest holders to complete. | CTM: | XReg: |  |  |  | XR handoff to CTMCo: | In Progress |  | Acronym to respond to Qs sent by DTR. [Owner]'s form is semi complete. [Owner] - Complete Waiting for [Owner]'s form [Owner] is a director/UBO - require form Della has uploaded forms to drive for review
3 | Part A - Form 3 (CEO/CO) (Required for SCB Approval in-principle) | Application for registration as CEO or Compliance Officer. | CTM: | CTM: |  |  |  | XR handoff to CTMCo: | In Progress |  | DTR uploaded forms for review by [Owner]
| Part A - Form 5 - Registration as Exchange (Required for SCB Approval in-principle) | [7 empty] | Completed |  | Outstanding matters - Form requires signature of the Treasuer - who would this be? Likely [Owner] - to be confirmed-- Treasurer--[Owner] --waiting for [Owner]s signture -- signed and uploaded
4 | Decision on Products/Services Mapping | XReg will conduct a product mapping exercise to develop a detailed understanding of each of the products and services offered by Acronym. This will identify all relevant parties and their roles, examine how the product is priced and settled, as well as its territorial availability, any potential issues, and recommendations. Based on this exercise, a decision will be made to include each in the licence application. | XReg: | XReg: |  |  |  | Products & Services Completion: April 23, 2024 | Completed |  | Completed
5 | Business Plan (Required for SCB Approval in-principle) | XReg to work with Acronym and provide as much input as necessary to develop the business plan to be submitted as part of the application. inc. financial and operational projections, staffing requirements, and technological requirements. | Acronym: | XReg: |  |  |  | Outline BP XR handoff to CTMCo: Full BP XR handoff to CTMCo: May 14, 2024 | In Progress |  | Mostly completed - couple of outstanding points to go over with [Owner] - [Owner]
6 | Evidence of the applicant’s good standing in accordance with section 277 of the Companies Act (Ch. 308) | CTM to register the company and submit a certificate of good standing as part of the application. | CTM: | Acronym: |  |  |  |  | Completed |  | Acronym to start transfer this week (Uploaded)
7 | Operational Capabilities (within the Form 1) | A detailed description of Acronym's operational capabilities, including the physical premises, cybersecurity protocols, data management systems, data protection systems, risk management systems, banking, digital clearing and digital custody arrangements, communication capabilities. XReg will assist in the collection of this data and completion of the form. | XReg: DM | XReg: |  |  |  |  | Completed |  | DM drafted. Acronym to review and fill in some areas. Still a couples of areas for [Owner] review
8 | Company incorporation documents | A certified copy of the applicant’s Memorandum and Articles of Association, or equivalent constitutive documents, and certificate of incorporation | CTM: | CTM: |  |  |  |  | Completed
9 | A schedule of proposed fees for services rendered by the business | Once decision on products/services has been made, Acronym will require a fee schedule based on these. XReg will assist in the development of this schedule by ensuring fees are consistent with the company's website, transparency within the business plan, and that they are itemised correctly. | XReg: | XReg: |  |  |  | XR Handoff to CTMCo: | Completed |  | DM uploaded template. [Owner] to fill in. [Owner] to finalise--finalized
10 | Evidence of the applicant’s registration with any other regulatory authority & Discipline History | Confirmation required that none of the people involved in Acronym have been disciplined by another regulatory authority, stock exchange, digital token exchange, or professional association in any jurisdiction. | XReg: |  |  |  |  | XR Handoff to CTMCo: | Not applicable/no longer required
11 | DD pre-check on all people named in all forms. | Xreg will undertake due diligence checks on all individuals involved in the application prior to the submission of forms. This will also involve an assessment of their CVs to ensure suitablitity with the roles in question. | XReg: | XReg: |  |  |  |  | Completed
12 | A copy of the Rules of the Exchange, including rules for admission to listing of digital assets on the exchange | Fees for membership, listing, execution of trades, clearing and settlement and any other charges. | [6 empty] | Completed |  | Drafted and ready for Acronym input and review DD questionnaire for issuers also included Reviwed and good to go.
13 | Financial Projections | Three to four year projections including projected income statement, projected balance sheet, and projected cash flow | Acronym: | XReg: |  |  |  | XR Handoff to CTMCo: | Completed |  | DM uploaded a template of example headings under Business Plan folder. Acronym to fill out
14 | Audited Financial Statements | For the two financial years immediately prior to the date of the application or, if shorter, since the date of establishment, the auditor's report accompanying the audited financial statements, and the interim financial statements for the prior two quarters, certified by the Chief Executive Officer (or equivalent) to be true and complete. | Acronym: | XReg: |  |  |  | XR Handoff to CTMCo: | In Progress |  | New entity - not part of existing group. No group accounts. Provide information on how the business is funded. [Owner] to provide this week. [Owner] to upload
15 | Confirmation of auditor and confirmation of banking partner | Confirmation from Acronym on who it intends to use as its financial auditor. This does not have to be an audit company resident in The Bahamas. Bahamas based bank to hold the regulatory capital. Onboarding has to be done with them. | Acronym: | [5 empty] | In Progress |  | DTR to send onboarding package (Fidelity) ahead of AIP and to connect with Auditors DTR emailed Fidelity pack - wont go in before approval in principle Auditors - HLB recommend - DTR introduced - To confirm with [Owner]
16 | Evidence of adequate Insurance & Regulatory Capital | Xreg to confirm with Acronym the insurance arrangements it proposes to hold. Xreg will also assess Acronym's proposal for capital requirements. This will involve holding a number of months of operating expenses to be able to ensure an orderly wind-down. Letter required confirming the funds are held in Escrow | Acronym: | XReg: |  |  |  | Acronym to XR - Evidence of regulatory capital: XR Handoff to CTMCo: | In Progress |  | DM uploaded as a tab on the financial projections template - Acronym to review
17 | Organizational Chart (with job descriptions for each position) and number of employees (Required for SCB Approval in-principle) | XReg to discuss with Acronym the roles that would be expected to be filled from a regulatory perspective and assist as necessary with preparation of chart and job descriptions. | Acronym: | XReg: |  |  |  | XR Handoff to CTMCo: | Completed |  | DM uploaded a template. [Owner] to send over updated version. Travel Rule provider to be listed [Owner] and [Owner] to sign and date document.
18 | Application Fee | Confirm with CTM that the relevant funds have been received to be sent to the Regulatory Authority for the submission of the applcation. | CTM: | XReg: |  |  |  | Acronym to CTMCo: | In Progress |  | DTR asking SCB for clarity Clarified - DTR to send invoice
19 | Terms and conditions for all products | XReg to review terms and conditions for all products and services to be offered by Acronym. | Acronym: | XReg: |  |  |  | XR Handoff to CTMCo: | In Progress |  | [Owner] to double check comments - resolve internal ones and flag to XR any external comments--comments resolved xreg to. review
20 | Company Name | Acronym to decide on a Company Name | Acronym: | [5 empty] | Completed
21 | Office Premises and Signed Lease Agreement |  | Acronym: | [5 empty] | Completed |  | [Owner] to send over - Crypto Isle (uploded on drive under company incopration file )
22 | Outsourcing Agreement(s) | Signed and dated | Acronym: | [5 empty] | Completed |  | [Owner] and [Owner] to send over - agreements with Perpetual Markets, Compliance monitorin [Owner] uploaded - XR to review Drata PMX Deel
23 | Register of Shareholders |  | Acronym: | [5 empty] | Completed |  | Transferring over to CTM--
24 | Sample Account Opening Forms (if applicable) | These forms should include: Identity, Financial Status, Employment, Education, Ability to incur risk, and other reasonable information for the firm to create a suitable investment recommendation | Acronym: | [5 empty] | Completed |  | Screenshots of account opening or explainer of each step. [Owner] to provide screenshots (Uploaded on Google drive)
25 | Recruitment of CEO |  | Acronym: | [5 empty] | Completed |  | [Owner]
26 | Recruitment of CO |  | Acronym: | [5 empty] | Completed |  | [Owner]
27 | Evidence of Board approval of the appointment of the CEO and Designated Compliance Officer | By way of a Board resolution | Acronym: | CTM: DTR |  |  |  | Acronym to CTMCo: | In Progress |  | [Owner] to send over to DTR. No communication from law firm - [Owner] to nudge--sent
28 | Statement from a senior officer | Confirming the applicant has not commenced trading since the date of establishment and that no financial statements have been produced or dividends declared; | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | In Progress |  | DTR thas uploaded to Google Drive. To be dated and signed by [Owner] closer to when we submit application
29 | No Objection Letter (Approval in Principle) | For products outside of the DARE Act | [6 empty] | Completed |  | Once P&S complete- XR to draft. [Owner] to review XR to finalise
Policies & Procedures
30 | AML/CFT Policy (Required for SCB Approval in-principle) | XReg will draft, tailor, or assess exisiting policies, logs, and registers for submission in this area. Policies will be cross checked against the business plan and sent to Acronym for review. For AML/CFT, this could include Acronym's policies for PEPs, CDD, sanctions, transaction monitoring etc. | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | Completed |  | JC reviewed - AJ final sign off
31 | AML Side Documents (Required for SCB Approval in-principle) | Customer Risk Score Calculator Business Risk Assessment Country Risk Schedule Onboarding procedures Migration Plan | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | Completed |  | JC reviewed - AJ final sign off
32 | Digital Token Management | As above For digital token management, this will include policies on private key management protocols. | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | Completed |  | Drafted and ready for Acronym review
33 | Safeguarding of Assets (Required for SCB Approval in-principle) | For safeguarding of assets, this will include policies on segregation of assets, any third party services used for this, and account designations for ring fencing. | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | Completed |  | XR reviewed
34 | Data Protection | For Data Protection, this will map out responsibilties, rules, subject rights, impact assessments, breach response plans, all in compliance with the Data Protection Privacy of Personal Infromation Act 2003 in The Bahamas. | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | Completed |  | Drafted and ready for Acronym review
35 | Cybersecurity |  | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | In Progress |  | Drafted and ready for Acronym review
36 | Internal Systems and Controls Manual |  | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | In Progress |  | Drafted and ready for Acronym review
37 | Reporting (Corporate Governance) (Required for SCB Approval in-principle) |  | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | Completed |  | Reviewed
38 | Code of Conduct (Corporate Governance) (Required for SCB Approval in-principle) | Conflicts of interest | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | Completed |  | Reviewed
39 | Business Continuity and Disaster Recovery | BCM Policy Business Continuity and Disaster Recovery Plan | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | In Progress |  | Plan is drafted and ready for review. BCM Policy drafted and ready for review
40 | Customer Care |  | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | Completed |  | Drafted and ready for Acronym review
41 | Marketing |  | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | In Progress |  | Drafted and ready for Acronym review
42 | Staking | Summary of terms of agreement specifying duties and responsibilties. Details of staking protocol, how assets are staked, rewards or interest earned, redemption, penalties etc. | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | In Progress |  | Drafted and ready for Acronym review and tailoring
43 | Internal Audit |  | XReg: | Acronym: |  |  |  | XReg to Acronym: (Review): To XReg for final review: XReg Handoff to CTMCo: | In Progress |  | Drafted and ready for Acronym review
Individuals
44 | Chief Executive Officer | 1. Copy of work permit or permanent residence permit with the right to work 2. Financial Reference (Relationship must be for at least three years) 3. Utility Bill (to confirm address) 4. Resume/CV 5. Copy of passport 6. Copy of professional qualifications 7. Police certificare/sworn affidavit for each jurisdiction of residence in the last 10 years 8. Confirmation of addresses over the last 10 years 9. Two character references 10. Recent photo | Acronym: | CTM: |  |  |  | Acronym to CTMCo: | Not Started |  | For AIP we need Nos. 2, 6 and 9. No. 1 will be applied for once AIP in hand We also need Board Approval of Appointment
45 | Compliance Officer/MLRO | 1. Copy of work permit or permanent residence permit with the right to work 2. Financial Reference (Relationship must be for at least three years) 3. Utility Bill (to confirm address) 4. Resume/CV 5. Copy of passport 6. Copy of professional qualifications 7. Police certificare/sworn affidavit for each jurisdiction of residence in the last 10 years 8. Confirmation of addresses over the last 10 years 9. Two Character references 10. Recent Photo | Acronym: | CTM: |  |  |  | Acronym to CTMCo: | Not Started |  | For AIP we need Nos. 2, 3, 4, 7, 9 and 10. No. 1 will be applied for once AIP in hand We also need Board Approval of Appointment
46 | Other Senior Officers named | 1. Copy of work permit or permanent residence permit with the right to work 2. Financial Reference (Relationship must be for at least three years) 3. Utility Bill (to confirm address) 4. Resume/CV 5. Copy of passport 6. Copy of professional qualifications 7. Police certificare/sworn affidavit for each jurisdiction of residence in the last 10 years 8. Confirmation of addresses over the last 10 years | Acronym: | CTM: |  |  |  | Acronym to CTMCo: | Not Started
47 | Directors | 1. Copy of work permit or permanent residence permit with the right to work 2. Financial Reference (Relationship must be for at least three years) 3. Utility Bill (to confirm address) 4. Resume/CV 5. Copy of passport 6. Copy of professional qualifications 7. Police certificare/sworn affidavit for each jurisdiction of residence in the last 10 years 8. Evidence of good standing with a professional association (if applicable) | Acronym: | CTM: |  |  |  | Acronym to CTMCo: | Not Started |  | [Owner] 1. is N/A We need 2 to 4 and 6 to 7. We also need Board Approval of Appointment [Owner]. is N/A We need 2 to 4 and 6 to 7. We also need Board Approval of Appointment. Note: renwed lease would suffice as proof of address. [Owner] (same as above)
48 | Beneficial Owners | 1. Copy of work permit or permanent residence permit with the right to work 2. Financial Reference (Relationship must be for at least three years) 3. Utility Bill (to confirm address) 4. Resume/CV 5. Copy of passport 6. Copy of professional qualifications 7. Police certificare/sworn affidavit for each jurisdiction of residence in the last 10 years 8. Evidence of good standing with a professional association (if applicable) | Acronym: | CTM: |  |  |  | Acronym to CTMCo: | Not Started
49 | Shareholder(s) | 1. Copy of work permit or permanent residence permit with the right to work 2. Financial Reference (Relationship must be for at least three years) 3. Utility Bill (to confirm address) 4. Resume/CV 5. Copy of passport 6. Copy of professional qualifications 7. Police certificare/sworn affidavit for each jurisdiction of residence in the last 10 years 8. Evidence of good standing with a professional association (if applicable) | Acronym: | CTM: |  |  |  | Acronym to CTMCo: | Not Started |  | [Owner] to send over table
50
51
Part A - Form 1: Required attachments:
1. Copy of the applicant’s written supervisory, internal controls and risk management policies and procedures.
2. A copy applicant’s detailed and up to date business plan, inclusive of financial and operational projections, staffing requirements, a description of products and/or services offered, target market, and technological requirements, etc.
3. Copies of required financial statements.
4. Evidence that the company has adequate insurance and regulatory capital.
5. An organizational chart for the firm together with job descriptions for each position. (Include total number of employees in the company).
6. Evidence of the applicant’s good standing in accordance with section 277 of the Companies Act (Ch. 308).
7. A certified copy of the applicant’s Memorandum and Articles of association, or equivalent incorporation documents.
8. A schedule of proposed fees for services rendered by the business.
9. Evidence of the applicant’s registration with any other regulatory authority, if applicable.
10. Completed Form 2 of the First Schedule in respect of each founder, beneficial owner, significant interest holder, director and officer of the applicant digital asset business.
[1] Note that where the Applicant is a publicly traded entity in The Bahamas or elsewhere, Form 2s are only required to be provided for significant interests holders of the Applicant.

## Project Status
Project Status
Project Status
Not Started
In Progress
Running Behind (no current risk of negative impact to schedule/ deadline
At Risk (possible risk of negative impact to schedule/deadline)
Stuck (delay agreed by all stakeholders)
Overdue (negative impact to schedule/deadline unless remediated)
Completed
Not applicable/no longer required